## Worksheet
Workflow Stage | Responsible Party | Timeline (Days) | Key Deliverables | KPIs & Metrics | Risk Assessment
Initiation | Project Sponsor & Steering Committee | 5 | Workflow scope document, Stakeholder map | Stakeholder alignment rate ≥ 90% | Scope ambiguity, resource gaps
Process Mapping | Process Analyst & Operations Team | 7 | Current state flowchart, pain point log | Mapping accuracy ≥ 95% | Inaccurate data inputs, incomplete processes
Gap Analysis | Quality Assurance & IT Teams | 5 | Process gaps report, efficiency benchmarks | Gap closure rate ≥ 85% | Underreported inefficiencies, data silos
Optimization Design | Process Improvement Team | 10 | Improved workflow design, automation plan | Cycle time reduction ≥ 20% | Technical feasibility issues, resistance to change
Pilot Implementation | Operations & IT Support | 14 | Pilot results summary, user feedback report | User adoption ≥ 80% | System errors, training gaps
Full-Scale Rollout | All Departments & Change Management | 21 | Go-live checklist, performance dashboard | Process efficiency improvement ≥ 30% | Integration issues, scalability concerns