## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Notes / Comments
Initiate Workflow Request | Project Manager | Mon, Apr 8, 2024 | Completed | Request submitted and approved by senior leadership.
Assign Tasks to Team | Operations Lead | Tue, Apr 9, 2024 | In Progress | Tasks distributed; team members confirmed.
Conduct Workflow Review | Quality Assurance Officer | Wed, Apr 10, 2024 | Pending | Review checklist to be completed.
Finalize Deliverables | Development Team | Thu, Apr 11, 2024 | Not Started | Deliverables under planning phase.
Submit for Approval | Project Manager | Fri, Apr 12, 2024 | Planned | Approval scheduled with stakeholders.
Post-Workflow Evaluation | Business Analyst | Sat, Apr 13, 2024 | Not Started | Metrics collection and feedback loop initiated.