## Worksheet
Date | Activity | Responsible Party | Status | Budget (USD) | Actual (USD)
2024-03-01 | Workflow Audit Initiation | Operations Team | Completed | 5,000.00 | 5,000.00
2024-03-15 | Process Mapping Phase | Process Analysts | In Progress | 8,000.00 | 3,200.00
2024-04-10 | Automation Proposal Review | <IT Department | Approved | 12,000.00 | 12,000.00
2024-05-15 | System Integration Testing | Dev Team | Pending Review | 15,000.00 | 9,800.00
2024-06-30 | Final Workflow Rollout | Project Manager | Scheduled | 20,000.00 | -
Total Budget (USD) |  |  |  |  | 50,000.00
Total Actual (USD) |  |  |  |  | 30,000.00