## Worksheet
Workflow Step | Activity Description | Resource Required | Estimated Time (hrs) | Cost (USD) | Cash Flow Impact | Status
Workflow Initiation | Define process goals and stakeholder inputs. | Project Manager, Stakeholders | 2 | $500 | +Initial Investment | Completed
Process Mapping | Document current workflows using BPMN diagrams. | Business Analyst, IT Team | 4.5 | $1,200 | +Tool Licensing | In Progress
Gap Analysis | Identify inefficiencies and bottlenecks. | Operations, Finance | 3 | $800 | +Diagnostic Cost | Planned
Automation Design | Design automated components using RPA or low-code tools. | DevOps, Software Engineers | 6 | $3,500 | +Development Cost | Pending Approval
Pilot Implementation | Run a controlled test in one department. | IT Support, Department Head | 5 | $1,800 | +Testing Cost | Scheduled
Full Rollout | Deploy workflow across all departments. | All Teams, Leadership | 10 | $6,000 | +Operational Cost (Ongoing) | Not Started
Performance Review | Measure KPIs and adjust as needed. | Analytics Team, Executives | 2.5 | $600 | -Maintenance & Optimization | Future Phase
Total Estimated Investment |  |  | 34.0 hrs | $13,400 | Net Cash Flow: -$13,400 (initial), +$5,800 (future savings)