## Worksheet
Task | Owner | Due Date | Status | Priority | Next Steps
Initiate Workflow Audit | Sarah Chen | 2024-04-15 | In Progress | High | Conduct stakeholder interviews and document current processes.
Map Process Flows | David Kim | 2024-04-22 | Not Started | High | Use BPMN to visualize key workflows and identify bottlenecks.
Identify Automation Opportunities | Lisa Moreno | 2024-05-01 | Not Started | Medium | Analyze repetitive tasks for potential RPA or script-based automation.
Define Optimization Goals | James Reed | 2024-04-28 | Not Started | High | Establish KPIs such as cycle time, error rate, and cost reduction.
Implement Pilot Workflow | Team Lead | 2024-06-10 | Planned | High | Roll out updated process in one department for 3 weeks of testing.
Evaluate Results & Refine | Sarah Chen | 2024-06-25 | Not Started | Medium | Review KPIs, gather feedback, and adjust workflow as needed.