## Worksheet
Task | Owner | Start Date | Due Date | Status | Priority | Dependencies | Notes/Remarks
Project Kickoff Meeting | John Doe | 2024-03-01 | 2024-03-05 | Completed | High | None | All team members were invited and objectives aligned.
Requirement Gathering | Sarah Chen | 2024-03-06 | 2024-03-15 | In Progress | High | Project Kickoff Meeting | Stakeholder interviews scheduled for Week 2.
Design Phase Initiation | Mike Roberts | 2024-03-16 | 2024-03-25 | Pending | Medium | Requirement Gathering Complete | Wireframes to be shared with stakeholders by Week 3.
Development Planning | Lisa Park | 2024-03-26 | 2024-04-10 | Not Started | High | Design Phase Initiation Complete | Tech stack finalized; sprint planning to begin.
Quality Assurance Setup | David Kim | 2024-04-11 | 2024-04-18 | Not Started | Medium | Development Planning Complete | Test environments configured; test cases drafted.
User Testing & Feedback | Emma Torres | 2024-04-19 | 2024-05-03 | Not Started | High | Quality Assurance Setup Complete | Beta users selected; feedback form distributed.
Final Review & Approval | Manager Team | 2024-05-04 | 2024-05-10 | Not Started | High | User Testing & Feedback Complete | All documentation finalized; sign-off required.