## Worksheet
Task | Owner | Due Date | Status | Budget Allocation ($) | Actual Cost ($) | Variance
Requirement Gathering | Jane Doe | 2024-03-15 | Completed | 15,000 | 14,200 | +800 (Under)
Process Mapping | John Smith | 2024-03-25 | In Progress | 10,000 | - | -
Workflow Redesign | Alice Brown | 2024-04-10 | Pending | 25,000 | - | -
Tool Implementation | Mike Lee | 2024-05-01 | Not Started | 30,000 | - | -
Performance Review | Sarah Wilson | 2024-05-30 | Completed | 8,000 | 7,950 | +50 (Under)
Total Budget ($) |  |  |  | 88,000