## Worksheet
Task | Owner | Due Date | Status | Next Step
Review Workflow Process | Alex Johnson | 2024-04-05 | In Progress | Share findings with team
Identify Bottlenecks | Sam Rivera | <->2024-04-12 | Pending | Conduct team review session
Propose Optimization Plan | Taylor Chen | 2024-04-19 | Not Started | Draft proposal by end of week
Team Feedback & Review | All Team Members | 2024-04-26 | Planned | Schedule virtual meeting
Finalize and Implement Changes | Project Lead | 2024-05-03 | Not Started | Execute changes in production