## Worksheet
Task | Owner | Due Date | Status | Progress (%) | Notes
Initiate Workflow Review | Sarah Chen | 2024-04-10 | Completed | 100% | All current workflows evaluated and documented.
Identify Bottlenecks | David Lee | 2024-04-15 | In Progress | 65% | Team meetings scheduled for review of approval delays.
Propose Process Improvements | Maria Garcia | 2024-04-25 | Not Started | 0% | Drafts to be developed after bottleneck analysis.
Conduct Pilot Testing | James Wilson | 2024-05-05 | Completed | 100% | Pilot successful with 95% efficiency gain.
Roll Out Optimized Workflow | Team Lead | 2024-05-15 | Pending Approval | 30% | Awaiting executive sign-off for full rollout.