## Worksheet
Workflow Step | Responsibility | Due Date | Status | Notes
Client Onboarding | Account Manager | 2024-04-15 | Completed | All documents submitted and verified.
Needs Assessment | Business Analyst | 2024-04-20In Progress | Initial survey sent to client; feedback pending.
Custom Workflow Design | Product Manager | 2024-05-05 | Planned | Draft workflow approved by stakeholders.
Client Training Session | Support Lead | 2024-05-15 | Pending | Date confirmed with client; materials ready.
Post-Implementation Review | Operations Team | 2024-06-10 | Not Started | Performance metrics to be collected.