## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Notes/Actions
Client Onboarding | Account Manager | Day 1 | Completed | Collect contact info, set up client portal.
Needs Assessment | Business Analyst | Day 3 | In Progress | Conduct discovery calls, draft scope document.
Process Design | Process Engineer | Day 7 | Pending | Finalize workflow diagrams and approval matrix.
Implementation Plan | Project Lead | Day 10 | Not Started | Coordinate team, assign tasks, define KPIs.
Training & Handover | Training Coordinator | Day 14 | Planned | Schedule sessions, create user manuals.
Performance Review | Client Success Manager | Day 30 | Not Started | Evaluate KPIs, gather feedback.