## Worksheet
Workflow Step | Client Engagement Action | Timeline (Days) | Responsibility | Status
Client Onboarding | Complete intake form, verify contact details, schedule initial meeting | 3 | Freelancer Lead (Manager) | Completed
Project Discovery | Conduct needs analysis, define deliverables, set expectations | 5 | Freelancer (Senior) | In Progress
Scope Finalization | Finalize project scope, create detailed deliverables list | 2 | Freelancer (Team Lead) | Pending
Kickoff Meeting | Host kickoff call with client to review plan and timeline | 1 | Freelancer (Project Manager) | Scheduled
Progress Reviews | Weekly check-ins to track progress, adjust deliverables if needed | Ongoing (Weekly) | Freelancer (Team Lead) | Active
Final Delivery & Sign-off | Submit final deliverables, obtain client approval and closeout | 3 | Freelancer (Senior) | Not Started