## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies
Client Onboarding | Sarah Johnson | 2024-04-15 | In Progress | High | N/A
Requirement Gathering | Mike Chen | 2024-04-25 | Not Started | High | Client Onboarding
Solution Design | Lena Rodriguez | 2024-05-10 | Planned | Medium | Requirement Gathering
Development Phase | Team A | 2024-06-01 | Not Started | High | Solution Design
Client Review & Approval | Sarah Johnson | 2024-06-15 | Pending | High | Development Phase
Go-Live & Training | Operations Team | 2024-07-01 | Not Started | Medium | Client Review & Approval