## Worksheet
Task ID | Workflow Stage | Owner | Due Date | Status | Estimated Cost | Actual Cost | Progress % | Notes
WF-001 | Lead Qualification | Sarah Thompson | 2024-04-15 | Completed | $1,200 | $1,150 | 100% | All leads screened; 37 qualified.
WF-002 | <Proposal Development | James Reed | 2024-04-25 | In Progress | $3,500 | $2,800 | 70% | Draft finalized; awaiting client feedback.
WF-003 | Client Negotiation | Lisa Chen | 2024-05-10 | Pending | $5,000 | $0 | 0% | Awaiting initial call with client.
WF-004 | Contract Finalization | Michael Ross | 2024-05-18 | Not Started | $2,300 | $0 | 0% | Waiting for client approval on proposal.