## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Notes
Identify key customer pain points | Sarah Chen | 2024-04-15 | In Progress | High | 65% | Initial survey results available; feedback from 120 customers.
Map customer journey stages | James Wilson | 2024-04-25 | Pending | Medium | 0% | Needs input from sales team for stage definitions.
Optimize lead routing rules | Linda Park | 2024-05-10 | Not Started | High | 0% | Review current CRM logic; propose automation improvements.
Schedule team alignment meeting | David Torres | 2024-04-20 | Completed | Low | 100% | Meeting conducted; action items documented.
Implement new workflow alerts | Maria Lopez | 2024-05-30 | Planned | High | 0% | System testing will begin in May.