## Worksheet
Task | Owner | Due Date | Status | Priority | Remarks
Customer Onboarding Setup | Sarah Johnson | 2024-04-15 | Completed | Medium | All required fields configured in CRM.
Lead Scoring Automation | Michael Chen | <# text-align: center;">2024-04-20In Progress | High | Integration with email campaigns in testing.
Follow-Up Email Sequence | Aisha Patel | 2024-04-25 | Pending | Medium | Draft reviewed by marketing team.
Reporting Dashboard Update | David Kim | 2024-05-01 | Not Started | High | Needs data source alignment with sales team.
CRM User Training Session | Team Lead | 2024-04-30 | Completed | Low | Scheduled for all new hires and team reps.