## Daily Planner - Tracking View
Workflow Optimization - Daily Planner (Tracking View)
Date | Task | Owner | Status | Priority | Estimated Time (mins) | < th>Actual Time (mins)Completion Notes
2023-10-05 | Review project timeline | Alex Chen | Completed | High | 45 | 42 | Slight delay due to client feedback.
2023-10-05 | Team stand-up meeting prep | Sarah Kim | In Progress | Moderate | 30 | - | Meeting scheduled for 10:00 AM.
2023-10-05 | Update risk register | David Lee | Pending | High | 60 | - | New risk identified during QA phase.
2023-10-06 | Client presentation draft review | Lisa Wong | Not Started | High | - | - | Waiting for feedback from design team.
2023-10-06 | Weekly performance report | John Reed | Completed | - | 35 | 35 | All KPIs within target range.