## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Budget Allocation (USD) | Notes
Needs Assessment | Client Relations Team | 2024-03-15 | On Track | $15,000 | Initial survey and stakeholder interviews completed.
Process Mapping | Operations Analyst | 2024-03-30 | In Progress | $12,500 | Mapping current workflows with process diagrams.
Gap Analysis | Strategy Office | 2024-04-10 | Pending | $8,000 | Identify inefficiencies and bottlenecks.
Solution Design | Product Innovation Team | 2024-04-25 | Not Started | $20,000 | Propose automation and redesign options.
Pilot Implementation | IT & Engineering | 2024-05-20 | Not Started | $18,500 | Test in one department before full rollout.
Full-Scale Rollout | Executive Leadership | 2024-06-30 | Not Started | $50,000 | Deploy across all departments with training.