## Worksheet
Workflow Step | Responsible Party | Duration (Days) | Resource Allocation | Key Metrics | Risk Assessment
Needs Assessment | Project Manager | 5 | 2 FTEs | Stakeholder feedback, ROI projection | Low - clear alignment with goals
Process Mapping | Operations Team | 7 | 1 FTE + Analyst | Current bottlenecks, handoff points | Medium - data accuracy dependency
Gap Analysis | Strategy Consultant | 6 | External expert (contract) | Efficiency gaps, compliance risks | High - requires external validation
Solution Design | Product & Engineering Teams | 12 | 4 FTEs (design + dev) | Cost vs. time, scalability | Medium - technical feasibility
Pilot Implementation | Operations & IT | 10 | 2 FTEs + Support Staff | Error rate, process velocity | Medium - scope limitations
Full-Scale Rollout | Executive Sponsor & Teams | 20 | 8 FTEs (distributed) | Adoption rate, KPI improvement | High - change management resistance
Review & Optimization | Project Manager & Analytics Team | 8 | 2 FTEs + Data Analyst | Cycle time, cost per transaction | Low - continuous improvement cycle