## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Key Deliverables | Dependencies | Risk Assessment | Approval Required?
Initiation & Scope Definition | Finance Director | 5 | Approved project scope, budget outline | - | Low | Yes
Process Mapping & Audit | Operations Manager | 7 | Current workflow diagrams, process gaps report | Scope Definition | Medium | Yes
Identify Optimization Opportunities | Finance Analyst Team | 10 | Optimization recommendations, cost-benefit analysis | Process Mapping | Medium | Yes
Stakeholder Workshops & Feedback | Project Lead | 6 | Feedback summary, validated improvement plan | Optimization Recommendations | Low | Yes
Implementation Plan & Rollout | IT & Finance Teams | 14 | Updated SOPs, training materials, rollout schedule | Workshops & Feedback | High | Yes
Monitoring & Performance Review | Finance Controller | Ongoing | KPI dashboard, monthly performance reports | Implementation Plan | Low | Yes (Monthly)