## Worksheet
Workflow Step | Responsible Party | Deadline | Required Documentation | Approval Required? | Status
Requirement Gathering | Finance Manager | 05/03/2024 | Project Scope Document, Budget Outline | Yes | Pending
Process Mapping | Operations Analyst | 05/10/2024 | Current Workflow Diagram, Stakeholder List | Yes | In Progress
Cost Analysis & Forecasting | Financial Analyst | 05/17/2024 | Historical Data, Market Trends Report | Yes | Not Started
Workflow Redesign Proposal | Process Improvement Team | 06/03/2024 | Draft Proposal, ROI Analysis | Yes | Planned
Stakeholder Review & Feedback | Project Steering Committee | 06/10/2024 | Feedback Summary, Draft Design Document | Yes | Scheduled
Implementation Plan Finalization | Finance & Operations Lead | 06/20/2024 | Final Implementation Schedule, Risk Assessment | Yes | Not Started
Total Workflow Steps |  |  |  | 6