## Worksheet
Workflow Step | Responsible Party | Deadline | Key Deliverable | Status | Notes
Requirement Gathering | Finance Analyst | 05/01/2024 | Detailed cost-benefit analysis | On Track | Include stakeholder feedback from operations.
Process Mapping | Operations Manager | 05/15/2024 | Visual workflow diagram (PDF) | In Progress | Pending final approval from HR.
Budget Allocation Review | Finance Director | 06/01/2024 | Approved budget sheet with variance analysis | Not Started | Needs alignment with departmental forecasts.
Implementation Plan | Project Lead | 06/30/2024 | Phased rollout schedule with KPIs | Planned | Include risk mitigation strategies.
Performance Monitoring | Finance & Compliance Team | Ongoing | Monthly performance reports | Not Started | Automated dashboard to be deployed.