## Worksheet
Workflow Phase | Current Status | Estimated Time (Days) | Cost Impact ($) | Resource Allocation | Action Required
Requirement Gathering | On Track | 7 | $5,200 | 3 Analysts | Review with Stakeholders (Q1)
Design & Prototyping | Delayed by 2 Days | 14 | $12,800 | 4 Designers + 1 Lead | Accelerate with Sprint Review
Development | On Track (Early) | 30 | $68,000 | 12 Developers + 2 QA | Weekly Code Reviews & Milestone Checks
Testing & Validation | Scheduled | 18 | $15,400 | 6 QA Engineers + 2 Test Leads | Initiate UAT in Week 6
Deployment & Handover | Pending Approval | 5 | $3,200 | Project Manager + Ops Team | Final Sign-Off from Client by EOD