## Worksheet
Workflow Phase | KPI Target | Current Performance | Variation (%) | Action Required | Responsibility
Requirement Gathering | 90% Completion in 5 Days | 85% | -5.6% | Improve stakeholder engagement | Project Manager
Design & Planning | 100% Approved in 7 Days | 95% | +5.0% | Continue quality reviews | Design Lead
Development Phase | No critical bugs by Day 25 | 80% | -20.0% | Introduce code reviews and testing | Engineering Team
Testing & QA | 98% Test Coverage | 92% | +2.0% | Expand regression suite | QA Manager
Deployment & Rollout | <100% User Adoption in 3 Days | 75% | -25.0% | Enhance onboarding process | Operations Team