## Worksheet
Workflow Stage | Current Status | Estimated Duration (Days) | Budget Allocation ($) | Resource Assignments | Key Milestones | Risk Level
Requirement Gathering | On Track | 10 | $25,000 | Project Manager, 2 Analysts | Final Scope Signed – Day 10 | Low
Design & Prototyping | In Progress | 15 | $40,000 | UX Designer, 1 Developer | Prototype Review – Day 15 | Medium
Development & Testing | Planned | 30 | $120,000 | Development Team (5), QA Lead | Beta Launch – Day 45 | High
Deployment & Monitoring | Not Started | 14 | $35,000 | IT Ops, Support Team | Go-Live – Day 75 | Medium
Post-Implementation Review | Planned | 7 | $10,000 | Project Manager, 1 Consultant | Final Evaluation – Day 82 | Low