## Worksheet
Workflow Stage | Current Status | Estimated Time (Days) | Resource Allocation | Cost Impact ($) | Optimization Action
Requirement Gathering | On Track | 5 | 3 FTEs | $15,000 | Standardize template usage
Design & Planning | Delayed (by 3 days) | 7 | 4 FTEs | $28,000 | Parallelize design review process
Development Phase | On Track | 14 | 6 FTEs | $84,000 | Implement automated testing pipeline
Quality Assurance | At Risk | 6 | 3 FTEs | $36,000 | Introduce AI-based defect detection
Deployment & Monitoring | On Track | 4 | 2 FTEs | $18,000 | Integrate real-time KPI tracking