## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed
Requirement Gathering | 2024-03-16 | 2024-04-10 | 35 | Business Analysts | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 | UI/UX Team | Planned
Development Phase | 2024-05-16 | 2024-07-31 | 86 | Development Team | Not Started
Testing & QA | 2024-08-01 | 2024-08-31 | 31 | QA Engineers | Scheduled
Deployment | 2024-09-01 | 2024-09-05 | 5 | DevOps Team | Not Started
Post-Implementation Review | 2024-09-06 | 2024-09-10 | 5 | Project Manager | Planned