## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | Jan 01, 2024 | Jan 15, 2024 | 15 | Project Manager | Completed
Workflow Analysis | Jan 16, 2024 | Feb 05, 2024 | 19 | Process Analyst | In Progress
Stakeholder Workshops | Feb 06, 2024 | Feb 28, 2024 | 23 | Team Lead | Planned
Process Redesign & Drafting | Mar 01, 2024 | Apr 15, 2024 | 65 | Design Team | Not Started
System Integration Planning | Apr 16, 2024 | May 30, 2024 | 45 | IT Manager | Scheduled
Pilot Testing Phase | Jun 01, 2024 | Jul 15, 2024 | 45 | QA Team | Planned
Full-Scale Deployment | Jul 16, 2024 | Aug 31, 2024 | 46 | Operations Team | Not Started
Post-Implementation Review | Sep 01, 2024 | Sep 30, 2024 | 30 | Project Manager | Scheduled
Annual Optimization Review | Oct 01, 2024 | Oct 31, 2024 | 31 | Executive Team | Planned