## Worksheet
Task | Start Date | End Date | Duration | Responsible Party | Status
Project Initiation | 2024-03-01 | 2024-03-10 | 10 days | Project Manager | Completed
Requirements Gathering | 2024-03-11 | 2024-03-25 | 15 days | Business Analysts | In Progress
Design Phase | 2024-03-26 | 2024-04-15 | 20 days | UI/UX Team | Not Started
Development Phase | 2024-04-16 | 2024-05-31 | 46 days | Development Team | Planned
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 days | QA Engineers | Not Started
Deployment & Go-Live | 2024-06-16 | 2024-06-25 | 10 days | IT Operations | Planned
Post-Launch Review & Optimization | 2024-06-26 | 2024-07-10 | 15 days | Project Manager & Team | Not Started