## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Project Manager | Completed
Requirement Gathering | 2024-03-16 | 2024-03-25 | 10 | Business Analysts | In Progress
Design Phase Finalization | 2024-03-26 | 2024-04-10 | 15 | UX/UI Team | Planned
Development Phase (Phase 1) | 2024-04-11 | 2024-05-15 | 35 | Development Team | Not Started
Testing & QA Validation | 2024-05-16 | 2024-06-05 | 20 | QA Team | Scheduled
Client Review & Final Approval | 2024-06-06 | 2024-06-15 | 10 | Client Representative | Pending
Go-Live Deployment | 2024-06-16 | 2024-06-18 | 3 | Operations Team | Not Started
Post-Implementation Review | 2024-06-19 | 2024-06-25 | 7 | Project Manager & Client | Planned