## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Progress (%)
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager | Completed | 100
Requirement Analysis | 2024-01-16 | 2024-02-15 | 30 | Business Analysts | 85 | 85
Design Phase | 2024-02-16 | 2024-03-31 | 46 | UX & UI Team | 70 | 70
Development Phase | 2024-04-01 | 2024-06-30 | 90 | Engineering Team | 50 | 50
Testing & QA | 2024-07-01 | 2024-07-31 | 31 | QA Team | 90 | 90
Deployment & Launch | 2024-08-01 | 2024-08-15 | 15 | IT Operations | Not Started | 0