## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Responsible Team | Dependencies | Status | Progress (%) | Milestones | Resources Required | Notes
WKF-001 | Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Management Office | None | Completed | 100% | Kickoff Completed | 1 Project Manager, 2 Facilitators
WKF-002 | Requirements Gathering & Analysis | 2024-03-02 | 2024-03-15 | 14 | Business Analysts Team | WKF-001 | In Progress | 70% |  | 5 Analysts, 3 Stakeholders | Final requirements to be reviewed by Steering Committee on 03-14.
WKF-003 | Process Mapping & Workflow Design | 2024-03-16 | 2024-04-10 | 35 | Process Design Team | WKF-002 | Planned | 0% |  | 3 Process Engineers, 2 UX Designers | Include integration points with legacy systems.
WKF-004 | Technical Architecture Review | 2024-04-11 | 2024-04-15 | 5 | Engineering Leadership | WKF-003 | Scheduled | 0% |  | Lead Architect, 2 Senior Engineers | Finalize cloud architecture and scalability plan.
WKF-005 | Development & Implementation | 2024-04-16 | 2024-07-15 | 91 | Development Team (Frontend & Backend) | WKF-004 | Not Started | 0% |  | 25 Developers, 5 QA Engineers | Phased rollout with MVP delivery by 06-30.
WKF-006 | Testing & Quality Assurance | 2024-07-16 | 2024-08-15 | 31 | QA & Testing Team | WKF-005 | Planned | 0% |  | 12 Testers, 3 Automation Experts | Include performance and security testing.
WKF-007 | User Training & Change Management | 2024-08-16 | 2024-09-30 | 45 | Training & Change Team | WKF-006 | Not Started | 0% |  | 5 Trainers, 2 Change Managers | Schedule in-person and virtual sessions for all departments.
WKF-008 | Go-Live & Post-Implementation Review | 2024-10-01 | 2024-10-15 | 15 | Operations & Support Team | WKF-007 | Planned | 0% | Go-Live Complete | 1 Support Team, 2 Operations Managers | Monitor KPIs and collect user feedback within first 30 days.