## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager | In Progress
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 | Business Analysts | Not Started
Design Phase | 2024-02-16 | 2024-03-31 | 56 | UI/UX Design Team | Planned
Development Phase | 2024-04-01 | 2024-06-30 | 91 | Software Developers | Not Started
Testing & QA | 2024-07-01 | 2024-08-15 | 46 | QA Team | Planned
Deployment & Go-Live | 2024-08-16 | 2024-08-31 | 16 | IT Operations | Not Started
Post-Implementation Review | 2024-09-01 | 2024-09-15 | 15 | Project Manager & Stakeholders | Not Started