## Worksheet
Task | Start Date | End Date | Duration (Days) | Assigned To | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Sarah Johnson | Completed
Requirement Gathering | 2024-04-02 | 2024-04-10 | 9 | Mark Lee | In Progress
Design Phase (Wireframes) | 2024-04-11 | 2024-04-18 | 8 | Lisa Wong | Not Started
Frontend Development | 2024-04-19 | 2024-05-15 | 28 | David Chen | Not Started
Backend Integration | 2024-05-16 | 2024-06-10 | 35 | Rachel Kim | Not Started
Testing & QA Review | 2024-06-11 | 2024-06-25 | 15 | James Patel | Not Started
User Training Sessions | 2024-06-26 | 2024-07-03 | 8 | Anna Flores | Not Started
Go-Live & Post-Implementation Review | 2024-07-04 | 2024-07-11 | 8 | Team Lead | Not Started