## Worksheet
Task ID | Task Name | Start Date | End Date
W0012024-01-152024-01-205-Project ManagerCompleted100%Full-time (1) |  |  |  | Duration (Days) | Predecessor | Responsible | Status | Progress (%) | Resource Allocation
W0022024-01-212024-02-1545W001Business Analysts (3)In Progress70%Part-time (2)
W0032024-02-162024-03-1530W002Lead Designer & Architects (2)Planned0%Full-time (1)
W0042024-03-162024-05-3185W003Development Team (8)Not Started0%Full-time (8)
W0052024-06-012024-06-3030W004QA Engineers (5)Not Started0%Full-time (5)
W0062024-07-012024-07-1515W005IT Operations (3)Planned0%Full-time (3)