## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Responsible Team | Budget Allocation ($) | Status | Progress (%)
Requirements Gathering | 2024-03-01 | 2024-03-15 | 15 | Product Strategy Team | 25,000 | Completed | 100%
Process Mapping & Analysis | 2024-03-16 | 2024-04-10 | 25 | Operations & Process Team | 35,000 | In Progress | 65%
Workflow Design & Prototyping | 2024-04-11 | 2024-05-15 | 35 | Design & Innovation Team | 40,000 | Planned | 0%
Pilot Implementation (Phase 1) | 2024-05-16 | 2024-06-30 | 45 | Technology & Deployment Team | 60,000 | Not Started | 0%
Full-Scale Deployment | 2024-07-01 | 2024-08-31 | 60 | Finance & Executive Leadership | 120,000 | Not Started | 0%