## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 day | Project Manager | Completed
Requirements Gathering | 2024-03-02 | 2024-03-10 | 9 days | Business Analyst | In Progress
Design Phase (UI/UX) | 2024-03-11 | 2024-03-25 | 15 days | UX Designer | Planned
Development Phase | 2024-03-26 | 2024-05-15 | 51 days | Development Team | Not Started
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 days | QA Engineer | Planned
Deployment & Launch | 2024-06-01 | 2024-06-05 | 5 days | DevOps Team | Not Started
Post-Launch Review | 2024-06-06 | 2024-06-10 | 5 days | Project Manager | Planned