## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Doe | Completed
Workflow Design | 2024-03-06 | 2024-03-15 | 10 | John Smith | In Progress
Process Validation | 2024-03-16 | 2024-03-25 | 10 | Lisa Chen | Not Started
User Training | 2024-03-26 | 2024-04-01 | 6 | Michael Brown | Planned
System Integration | 2024-04-02 | 2024-04-15 | 14 | Sarah Lee | Not Started
Final Review & Optimization | 2024-04-16 | 2024-04-20 | 5 | Jane Doe | Not Started