## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Strategy & Operations | Completed
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-10 | 35 | Product & UX Team | In Progress
Design Phase (Wireframes & Prototypes) | 2024-04-11 | 2024-05-05 | 35 | Design & Creative | Planned
Development & Integration | 2024-05-06 | 2024-07-15 | 71 | Engineering Team | Not Started
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | QA & DevOps | Not Started
Deployment & Go-Live | 2024-08-11 | 2024-08-15 | 5 | Operations & Support | Not Started
Post-Launch Review & Optimization | 2024-08-16 | 2024-09-05 | 20 | Analytics & Strategy | Planned