## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Manager | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Sarah Johnson | On Track
Requirement Gathering | 2024-03-16 | 2024-04-10 | 35 | David Chen | On Track
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Lisa Martinez | Delayed (Review)
Development | 2024-05-16 | 2024-07-10 | 65 | James Wilson | On Track
Testing & QA | 2024-07-11 | 2024-08-15 | 45 | Emma Taylor | Pending Review
Deployment & Go-Live | 2024-08-16 | 2024-08-31 | 16 | Robert Kim | Planned