## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Requirements Gathering | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed
Workflow Design & Prototyping | 2024-03-16 | 2024-04-10 | 35 | UX Designer | In Progress
Stakeholder Review & Feedback | 2024-04-11 | 2024-04-18 | 8 | Client Reps | Pending
System Integration Planning | 2024-04-19 | 2024-05-10 | 33 | IT Lead | Not Started
Pilot Deployment (Month 1) | 2024-05-11 | 2024-05-31 | 31 | Operations Team | Scheduled
Performance Monitoring & Adjustments | 2024-06-01 | 2024-06-30 | 30 | Data Analysts | Not Started