## Worksheet
Task ID | Task Name | Start Date | End Date | Dur (Days) | Predecessor | Status
W1-001 | Define Workflow Objectives | 2024-03-01 | 2024-03-15 | 15 | - | Planned
W1-002 | <Map Current Workflow Process | 2024-03-16 | 2024-03-31 | 16 | W1-001 | In Progress
W1-003 | <Identify Bottlenecks & Risks | 2024-04-01 | 2024-04-15 | 15 | W1-002 | Pending Review
W1-004 | <Design Optimized Workflow | 2024-04-16 | 2024-05-15 | 31 | W1-003 | Not Started
Page 1 of Multi-Page Gantt Chart
W1-005 | Develop Workflow Documentation | 2024-05-16 | 2024-06-15 | 31 | W1-004 | Pending Approval
W1-006 | <Conduct Stakeholder Review & Feedback Loop | 2024-06-16 | 2024-07-15 | 31 | W1-005 | Scheduled
W1-007 | <Implement Workflow Changes in Production | 2024-07-16 | 2024-08-31 | 57 | W1-006 | Planned
Page 2 of Multi-Page Gantt Chart
W1-008 | Monitor Performance & KPIs Post-Implementation | 2024-09-01 | 2024-10-31 | 63 | W1-007 | Pending Start
Page 3 of Multi-Page Gantt Chart