## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Smith | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Sarah Lee | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Mike Johnson | Planned
Development Phase | 2024-05-16 | 2024-07-31 | 86 | Team A | Not Started
Testing & QA | 2024-08-01 | 2024-09-15 | 65 | Lisa Brown | Planned
Deployment & Launch | 2024-09-16 | 2024-10-05 | 20 | David Chen | Scheduled