## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Smith | Completed
Requirement Gathering | 2024-03-06 | 2024-03-15 | 10 | Mark Johnson | In Progress
Design Phase | 2024-03-16 | 2024-03-28 | 13 | Sarah Lee | Not Started
Development Phase | 2024-03-29 | 2024-04-15 | 18 | David Chen | Planned
Testing & Quality Assurance | 2024-04-16 | 2024-04-30 | 15 | Lisa Wong | Not Started
Deployment & Launch | 2024-05-01 | 2024-05-05 | 5 | Robert Kim | Not Started