## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 day | Project Manager | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 days | Business Analysts | In Progress
Workflow Design & Prototyping | 2024-03-16 | 2024-03-31 | 16 days | UX & Development Team | Not Started
System Development & Integration | 2024-04-01 | 2024-05-15 | 66 days | Engineering Team | Planned
Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 days | QA Team | Not Started
User Training & Documentation | 2024-06-11 | 2024-06-25 | 15 days | Training Specialist | Planned
Go-Live & Post-Implementation Review | 2024-06-26 | 2024-07-05 | 10 days | Project Manager & Operations Team | Not Started