## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Business Analysts | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 | UX & UI Team | Planned
Development | 2024-05-16 | 2024-08-31 | 117 | Software Developers | Not Started
Testing & QA | 2024-09-01 | 2024-10-15 | 60 | QA Team | Planned
Deployment | 2024-10-16 | 2024-10-31 | 16 | DevOps Team | Not Started
Post-Deployment Review | 2024-11-01 | 2024-11-15 | 15 | Project Manager | Planned