## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 days | Project Manager | Completed
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 days | Business Analyst | In Progress
Design Phase | 2024-03-16 | 2024-03-31 | 16 days | UI/UX Designer | Planned
Development | 2024-04-01 | 2024-05-30 | 60 days | Software Engineers | Not Started
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 days | QA Team | Planned
Deployment & Training | 2024-07-01 | 2024-07-15 | 15 days | IT Operations | Not Started
Post-Implementation Review | 2024-07-16 | 2024-07-25 | 10 days | Project Manager | Planned