## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Quarterly Strategy Review | 2024-01-01 | 2024-01-15 | 15 | Operations Director | Completed
Workflow Process Mapping | 2024-01-16 | 2024-02-15 | 30 | Process Analyst Team | In Progress
Identify Bottlenecks | 2024-02-16 | 2024-03-15 | 30 | Operations Team | Planned
Propose Optimization Solutions | 2024-03-16 | 2024-04-15 | 30 | Productivity Lead | Not Started
Pilot Implementation (Phase 1) | 2024-04-16 | 2024-05-31 | 46 | Engineering & Support Teams | Planned
Evaluate Performance Metrics | 2024-06-01 | 2024-06-30 | 30 | Data Analytics Team | Not Started
Final Workflow Adjustments | 2024-07-01 | 2024-07-31 | 31 | Operations Director | Planned