## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed
Requirement Gathering | 2024-03-16 | 2024-04-10 | 35 | Business Analysts | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 | UI/UX Design Team | Not Started
Development Phase | 2024-05-16 | 2024-08-31 | 117 | Software Development Team | Planned
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 65 | QA Team | Not Started
Deployment & Go-Live | 2024-10-16 | 2024-10-31 | 16 | IT Operations Team | Planned
Post-Implementation Review | 2024-11-01 | 2024-11-30 | 30 | Project Manager & Stakeholders | Not Started