## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Manager | Completed
Market Research & Analysis | 2024-04-02 | 2024-04-10 | 9 | Marketing Team | In Progress
Product Requirement Definition | 2024-04-11 | 2024-04-18 | 8 | Product Owner | Pending
UI/UX Design Phase | 2024-04-19 | 2024-05-03 | 15 | Design Team | Not Started
Development Phase (Phase 1) | 2024-05-04 | 2024-05-18 | 15 | Engineering Team | Not Started
Testing & Quality Assurance | 2024-05-19 | 2024-06-03 | 15 | QA Team | Not Started
Client Review & Feedback | 2024-06-04 | 2024-06-11 | 8 | Client & Manager | Not Started
Final Deployment & Go-Live | 2024-06-12 | 2024-06-15 | 4 | IT Operations | Not Started